## Slide 1
🦅 Raptor — Roadmap & Status
Phased Delivery | DACI Status | Current Progress | Next Steps
SAILPOINT | DATA PLATFORM
March 2026 | Confidential

## Slide 2
Phased Delivery Roadmap
SAILPOINT | RAPTOR PROJECT
Phase I
Prove It Works
Q4'25 - Q1'26
• Validate each lane via POCs
• Joint observability dashboards
• Runbooks & cost models
• ALT decision gate: continue/pivot/pause
Phase II
Golden Paths
Q2'26
• Documented Kafka→Store→GraphQL flows
• Schema & SLO templates
• First product integration
• MySailPoint or Access Center
Phase III
Self-Service
Q3'26
• Prebuilt templates
• Onboarding guides & cost dashboards
• Internal workshops
• Scale early adopters
Phase IV
Scale & Harden
Q4'26+
• External GraphQL exposure
• FedRAMP readiness
• Cost optimization
• SLO enforcement
◀ WE ARE HERE

## Slide 3
DACI Decision Status & POC Progress
SAILPOINT | RAPTOR PROJECT
🌐
GraphQL Layer
Apollo Router + Federation 2
📝 Draft
SAASD8NG-4502
Stand up router, first subgraph integrated
⚡
Pointed Lookups
ScyllaDB (self-hosted + Cloud)
🔄 In Progress
SAASD8NG-4501
p95 ≤ 10ms @ 5K RPS, cost ↓ 30%
🔗
Graph Database
JanusGraph on Scylla
🔄 In Progress
SAASD8NG-4273
p95 < 1s for N-hop, 5B edges scale
📊
Real-Time Analytics
ClickHouse (self-hosted/SaaS)
📝 Draft
SAASD8NG-4972
p95 < 300ms, cost ↓ 40% vs SF
🔍
Search Layer
Aperture Search subgraph
📝 Draft
—
Search 2.0 strategy, contract compatibility
Driver: Derrick Mink (departed) → Ownership gap to be addressed | Approvers: Dan Sparks, Fuad Rashid | INIT-2073: In Progress

## Slide 4
Risks, Mitigations & Immediate Actions
SAILPOINT | RAPTOR PROJECT
⚠️ Driver Departed
Derrick Mink left — ownership gap
across all DACI lanes
✅ Assign new drivers per lane
immediately
🚧 DevOps Bottleneck
Infrastructure intake can block
POC velocity
✅ Pre-stub stories, align early
with SRE teams
🏗️ Infra Complexity
Self-hosted DBs require ops
expertise
✅ Evaluate SaaS alternatives
in parallel
👥 Team Capacity
Limited bandwidth for
multi-lane POCs
✅ Engage evolv/tiger teams
for environment setup
⚡ Immediate Next Steps:
1️⃣ Assess current POC state — what's deployed & running
2️⃣ Clarify ownership — new drivers for each DACI lane
3️⃣ Address DPINTAKE-33 — delivery date for Identity Graph
4️⃣ Unblock backlog — assign subgraph stories 5980/5981/5982
5️⃣ Rename to Raptor — update Confluence, Jira, Slack
6️⃣ Establish weekly cadence — "Raptor Updates" posts
7️⃣ Schedule kickoff sync — Forge, Keel, DIPO, Double Zero

## Slide 5
Let's Move Forward
Raptor: From POC to Production
📧 dattu.marneni@sailpoint.com | 📋 DPINTAKE-33 | 💬 #raptor-data-platform